## Techite
| The scope of this project is directly from 2011 CIP |  |  |  |  | Techite Pipe + 1 Upstream VCP
Item | Description - Techite Pipe Rehab (OVT near Grande Vista) G-20-05 to G-19-06 | Cost |  |  |  | 8in | 10in | 12in | 15in | 18in | 21in | 24in | Enter Values for Yellow Cells
1.01 | Design | 24000 |  | Small, simple design @ 5% | Length: | 0 | 0 | 0 | 966 | 740 | 0 | 0 |  | 8in | 10in | 12in | 15in | 18in | 21in | 24in
1.02 | Environmental Design | 0 |  |  | CCTV: | 0 | 0 | 0 | 11592 | 11100 | 0 | 0 | Rehab. Cost per Ft 2025 Estimate | 50 | 60 | 100 | 200 | 225 | 250 | 300
2.01 | Temporary and/or Permanent Easements | 0 |  | No easements anticipated | Rehab: | 0 | 0 | 0 | 193200 | 166500 | 0 | 0 | CCTV/Prep Cost per Ft 2025 Estimate | 10 | 10 | 10 | 12 | 15 | 15 | 20
2.02 | Permits (ROW, VCWPD, 401, 404, etc.) | 1000 |  | Assume each project is $1M and needs a $2,500 permit | [8 empty] | Avg prop line (dense) | 75
3.01 | Construction Management | 24000 |  | CM assistance at 5% | No. MHs: | 6 | [6 empty] | Avg prop line (rural) | 200
3.02 | Construction Phase Services | 12000 |  | CPS at 2.% | Rehab Cost / MH inc. TC: | 7500 | [6 empty] | Sewer Lateral Re-establishment | 1500
3.03 | Inspection | 17000 |  | Contract inspection | [8 empty] | Sewer Lateral Insert | 4000
3.04 | Material Testing | 0 |  | No paving, MH testing included in price | [8 empty] | Traffic Control / Day (Minor) | 1500
4.01 | Restoration | 0 |  | No restoration anticipated. | [8 empty] | Traffic Control / Day (Significant) | 3000
4.02 | Mitigation | 0 |  | No mitigation anticipated | [8 empty] | Traffic Control / Day (Caltrans) | 3500
5.01 | Mobilization | 23000 | [10 empty] | Point Repair Est. | 10000
5.02 | Traffic Control (reduced to half minor TC cost) | 10000 | [10 empty] | Inspection / Day | 1760
5.03 | Point Repairs | 17000
5.04 | CCTV Inspection and Pipe Preparation | 23000
5.05 | Sewer Main Lining | 360000
5.06 | Sewer Lateral Re-Establishment / Lateral Inserts | 0 |  | None
5.07 | Manhole Rehabilitation | 45000
6.01 | Closeout, As-builts | 4000
| TOTAL | 560000 | 0
| Design and Environmental | 25000
| Inspection and Construction Management | 53000
| Construction and Closeout | 482000
| Total Cost | 560000

## 2026 Pipe Bursting-v1
Item | Description - Rancho Dr and Alto/Feliz Dr Pipe Bursting | Cost |  | Comments / Assumptions | [9 empty] | Enter Values for Yellow Cells
1.01 | Design | 89000 |  | Small, simple design @ 7.5% |  | 6in | 8in | 10in | 12in | 15in | 18in | 21in | 24in |  | 6in | 8in | 10in | 12in | 15in | 18in | 21in | 24in
1.02 | Environmental Design | 0 |  | Anticipate need for arborist report ($50k + $50k over time) | Length: | 3810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Rehab. Cost per Ft 2025 Estimate | 75 | 50 | 60 | 100 | 200 | 225 | 250 | 300
2.01 | Temporary and/or Permanent Easements | 0 |  | No easements anticipated | CCTV: | 57150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Bursting Cost per Ft Estimate | 275 | 275 | 300 | 325 | 350 | 450 | 500 | 600
2.02 | Permits (ROW, VCWPD, 401, 404, etc.) | 3000 |  | Assume each project is $1M and needs a $2,500 permit | Rehab (Lining): | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CCTV/Prep Cost per Ft 2025 Estimate | 15 | 10 | 10 | 10 | 12 | 15 | 15 | 20
3.01 | Construction Management | 60000 |  | CM assistance at 5% | Bursting: | 1047750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Avg prop line (dense) | 75
3.02 | Construction Phase Services | 60000 |  | CPS at 5% | [9 empty] | Avg prop line (rural) | 200
3.03 | Inspection | 50000 |  | Contract inspection | [9 empty] | Sewer Lateral Re-establishment | 1500
3.04 | Material Testing | 8000 |  | Testing for final A/C paving in bursting area |  | 3810 | [7 empty] | Sewer Lateral Insert | 4000
4.01 | Restoration | 0 |  | Restoration embedded in constructon. No major restoration projects anticipated. | [9 empty] | Traffic Control / Day (Minor) | 1500
4.02 | Mitigation | 0 |  | No mitigation anticipated | [9 empty] | Traffic Control / Day (Significant) | 3000
5.01 | Mobilization | 57000 |  | Note: this will be separate D&C projects over many years | [9 empty] | Traffic Control / Day (Caltrans) | 3500
5.02 | Traffic Control | 29000 |  | TC complex in MO. 400 LF/day CIPP, 150 LF/day bursting. | [9 empty] | Point Repair Est. | 10000
5.03 | Point Repairs | 0 |  | High GW in MO per 2014 I&I study. May be required in CIPP and bursting area. | [9 empty] | Point Repair High GW | 15000
5.04 | CCTV Inspection and Pipe Preparation | 57000 | [11 empty] | Inspection / Day | 1760
5.05 | Sewer Main Lining (>6in) | 0
5.06 | Sewer Main Bursting (6in) inc. Lateral Connection | 1048000 |  | Note: may be more practical to open trench due to short P/Ls in MO
5.07 | Sewer Lateral Re-Establishment (CIPP only) | 0
5.08 | Sewer Lateral Insert (CIPP only) | 0
6.1 | Closeout, As-builts | 7000
| TOTAL | 1470000 | 0
| Design and Environmental | 92000
| Inspection and Construction Management | 170000
| Construction and Closeout | 1206000
| Total Cost | 1468000
1

## 2026 PB-Rancho Only
Item | Description - Rancho Dr and Alto/Feliz Dr Pipe Bursting | Cost |  | Comments / Assumptions | [9 empty] | Enter Values for Yellow Cells
1.01 | Design | 35000 |  | Small, simple design @ 7.5% |  | 6in | 8in | 10in | 12in | 15in | 18in | 21in | 24in |  | 6in | 8in | 10in | 12in | 15in | 18in | 21in | 24in
1.02 | Environmental Design | 0 |  | Anticipate need for arborist report ($50k + $50k over time) | Length: | 1490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Rehab. Cost per Ft 2025 Estimate | 75 | 50 | 60 | 100 | 200 | 225 | 250 | 300
2.01 | Temporary and/or Permanent Easements | 0 |  | No easements anticipated | CCTV: | 22350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Bursting Cost per Ft Estimate | 275 | 275 | 300 | 325 | 350 | 450 | 500 | 600
2.02 | Permits (ROW, VCWPD, 401, 404, etc.) | 1000 |  | Assume each project is $1M and needs a $2,500 permit | Rehab (Lining): | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CCTV/Prep Cost per Ft 2025 Estimate | 15 | 10 | 10 | 10 | 12 | 15 | 15 | 20
3.01 | Construction Management | 23000 |  | CM assistance at 5% | Bursting: | 409750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Avg prop line (dense) | 75
3.02 | Construction Phase Services | 23000 |  | CPS at 5% | [9 empty] | Avg prop line (rural) | 200
3.03 | Inspection | 20000 |  | Contract inspection | [9 empty] | Sewer Lateral Re-establishment | 1500
3.04 | Material Testing | 3000 |  | Testing for final A/C paving in bursting area |  | 1490 | [7 empty] | Sewer Lateral Insert | 4000
4.01 | Restoration | 0 |  | Restoration embedded in constructon. No major restoration projects anticipated. | [9 empty] | Traffic Control / Day (Minor) | 1500
4.02 | Mitigation | 0 |  | No mitigation anticipated | [9 empty] | Traffic Control / Day (Significant) | 3000
5.01 | Mobilization | 22000 |  | Note: this will be separate D&C projects over many years | [9 empty] | Traffic Control / Day (Caltrans) | 3500
5.02 | Traffic Control | 11000 |  | TC complex in MO. 400 LF/day CIPP, 150 LF/day bursting. | [9 empty] | Point Repair Est. | 10000
5.03 | Point Repairs | 0 |  | High GW in MO per 2014 I&I study. May be required in CIPP and bursting area. | [9 empty] | Point Repair High GW | 15000
5.04 | CCTV Inspection and Pipe Preparation | 22000 | [11 empty] | Inspection / Day | 1760
5.05 | Sewer Main Lining (>6in) | 0
5.06 | Sewer Main Bursting (6in) inc. Lateral Connection | 410000 |  | Note: may be more practical to open trench due to short P/Ls in MO
5.07 | Sewer Lateral Re-Establishment (CIPP only) | 0
5.08 | Sewer Lateral Insert (CIPP only) | 0
6.1 | Closeout, As-builts | 3000
| TOTAL | 580000 | 0
| Design and Environmental | 36000
| Inspection and Construction Management | 66000
| Construction and Closeout | 471000
| Total Cost | 573000
1

## 2026 PB-Alto Only
Item | Description - Rancho Dr and Alto/Feliz Dr Pipe Bursting | Cost |  | Comments / Assumptions | [9 empty] | Enter Values for Yellow Cells
1.01 | Design | 43000 |  | Small, simple design @ 7.5% |  | 6in | 8in | 10in | 12in | 15in | 18in | 21in | 24in |  | 6in | 8in | 10in | 12in | 15in | 18in | 21in | 24in
1.02 | Environmental Design | 0 |  | Anticipate need for arborist report ($50k + $50k over time) | Length: | 1830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Rehab. Cost per Ft 2025 Estimate | 75 | 50 | 60 | 100 | 200 | 225 | 250 | 300
2.01 | Temporary and/or Permanent Easements | 0 |  | No easements anticipated | CCTV: | 27450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Bursting Cost per Ft Estimate | 275 | 275 | 300 | 325 | 350 | 450 | 500 | 600
2.02 | Permits (ROW, VCWPD, 401, 404, etc.) | 1000 |  | Assume each project is $1M and needs a $2,500 permit | Rehab (Lining): | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CCTV/Prep Cost per Ft 2025 Estimate | 15 | 10 | 10 | 10 | 12 | 15 | 15 | 20
3.01 | Construction Management | 29000 |  | CM assistance at 5% | Bursting: | 503250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Avg prop line (dense) | 75
3.02 | Construction Phase Services | 29000 |  | CPS at 5% | [9 empty] | Avg prop line (rural) | 200
3.03 | Inspection | 24000 |  | Contract inspection | [9 empty] | Sewer Lateral Re-establishment | 1500
3.04 | Material Testing | 4000 |  | Testing for final A/C paving in bursting area |  | 1830 | [7 empty] | Sewer Lateral Insert | 4000
4.01 | Restoration | 0 |  | Restoration embedded in constructon. No major restoration projects anticipated. | [9 empty] | Traffic Control / Day (Minor) | 1500
4.02 | Mitigation | 0 |  | No mitigation anticipated | [9 empty] | Traffic Control / Day (Significant) | 3000
5.01 | Mobilization | 27000 |  | Note: this will be separate D&C projects over many years | [9 empty] | Traffic Control / Day (Caltrans) | 3500
5.02 | Traffic Control | 14000 |  | TC complex in MO. 400 LF/day CIPP, 150 LF/day bursting. | [9 empty] | Point Repair Est. | 10000
5.03 | Point Repairs | 0 |  | High GW in MO per 2014 I&I study. May be required in CIPP and bursting area. | [9 empty] | Point Repair High GW | 15000
5.04 | CCTV Inspection and Pipe Preparation | 27000 | [11 empty] | Inspection / Day | 1760
5.05 | Sewer Main Lining (>6in) | 0
5.06 | Sewer Main Bursting (6in) inc. Lateral Connection | 503000 |  | Note: may be more practical to open trench due to short P/Ls in MO
5.07 | Sewer Lateral Re-Establishment (CIPP only) | 0
5.08 | Sewer Lateral Insert (CIPP only) | 0
6.1 | Closeout, As-builts | 3000
| TOTAL | 710000 | 0
| Design and Environmental | 44000
| Inspection and Construction Management | 82000
| Construction and Closeout | 578000
| Total Cost | 704000
1

## 2026 PB-Feliz Only
Item | Description - Rancho Dr and Alto/Feliz Dr Pipe Bursting | Cost |  | Comments / Assumptions | [9 empty] | Enter Values for Yellow Cells
1.01 | Design | 11000 |  | Small, simple design @ 7.5% |  | 6in | 8in | 10in | 12in | 15in | 18in | 21in | 24in |  | 6in | 8in | 10in | 12in | 15in | 18in | 21in | 24in
1.02 | Environmental Design | 0 |  | Anticipate need for arborist report ($50k + $50k over time) | Length: | 490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Rehab. Cost per Ft 2025 Estimate | 75 | 50 | 60 | 100 | 200 | 225 | 250 | 300
2.01 | Temporary and/or Permanent Easements | 0 |  | No easements anticipated | CCTV: | 7350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Bursting Cost per Ft Estimate | 275 | 275 | 300 | 325 | 350 | 450 | 500 | 600
2.02 | Permits (ROW, VCWPD, 401, 404, etc.) | 0 |  | Assume each project is $1M and needs a $2,500 permit | Rehab (Lining): | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CCTV/Prep Cost per Ft 2025 Estimate | 15 | 10 | 10 | 10 | 12 | 15 | 15 | 20
3.01 | Construction Management | 8000 |  | CM assistance at 5% | Bursting: | 134750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Avg prop line (dense) | 75
3.02 | Construction Phase Services | 8000 |  | CPS at 5% | [9 empty] | Avg prop line (rural) | 200
3.03 | Inspection | 6000 |  | Contract inspection | [9 empty] | Sewer Lateral Re-establishment | 1500
3.04 | Material Testing | 1000 |  | Testing for final A/C paving in bursting area |  | 490 | [7 empty] | Sewer Lateral Insert | 4000
4.01 | Restoration | 0 |  | Restoration embedded in constructon. No major restoration projects anticipated. | [9 empty] | Traffic Control / Day (Minor) | 1500
4.02 | Mitigation | 0 |  | No mitigation anticipated | [9 empty] | Traffic Control / Day (Significant) | 3000
5.01 | Mobilization | 7000 |  | Note: this will be separate D&C projects over many years | [9 empty] | Traffic Control / Day (Caltrans) | 3500
5.02 | Traffic Control | 4000 |  | TC complex in MO. 400 LF/day CIPP, 150 LF/day bursting. | [9 empty] | Point Repair Est. | 10000
5.03 | Point Repairs | 0 |  | High GW in MO per 2014 I&I study. May be required in CIPP and bursting area. | [9 empty] | Point Repair High GW | 15000
5.04 | CCTV Inspection and Pipe Preparation | 7000 | [11 empty] | Inspection / Day | 1760
5.05 | Sewer Main Lining (>6in) | 0
5.06 | Sewer Main Bursting (6in) inc. Lateral Connection | 135000 |  | Note: may be more practical to open trench due to short P/Ls in MO
5.07 | Sewer Lateral Re-Establishment (CIPP only) | 0
5.08 | Sewer Lateral Insert (CIPP only) | 0
6.1 | Closeout, As-builts | 1000
| TOTAL | 190000 | 0
| Design and Environmental | 11000
| Inspection and Construction Management | 22000
| Construction and Closeout | 155000
| Total Cost | 188000
1

## OCR Rehab
Old Creek Road to GSC
Item | Description - Trunk Sewer Rehab. (Old Creek Rd I-19-02 to H-18-08) | Cost |  |  |  | 8in | 10in | 12in | 15in | 18in | 21in | 24in | Enter Values for Yellow Cells
1.01 | Design | 73000 |  | Small, simple design @ 7.5% | Length: | 0 | 0 | 0 | 0 | 0 | 2480 | 0 |  | 8in | 10in | 12in | 15in | 18in | 21in | 24in
1.02 | Environmental Design | 0 |  |  | CCTV: | 0 | 0 | 0 | 0 | 0 | 37200 | 0 | Rehab. Cost per Ft 2025 Estimate | 50 | 60 | 100 | 200 | 225 | 250 | 300
2.01 | Temporary and/or Permanent Easements | 0 |  | No easements anticipated | Rehab: | 0 | 0 | 0 | 0 | 0 | 620000 | 0 | CCTV/Prep Cost per Ft 2025 Estimate | 10 | 10 | 10 | 12 | 15 | 15 | 20
2.02 | Permits (ROW, VCWPD, 401, 404, etc.) | 2000 |  | Assume each project is $1M and needs a $2,500 permit | [8 empty] | Avg prop line (dense) | 75
3.01 | Construction Management | 98000 |  | CM assistance at 10% | [8 empty] | Avg prop line (rural) | 200
3.02 | Construction Phase Services | 49000 |  | CPS at 5% | [8 empty] | Sewer Lateral Re-establishment | 1500
3.03 | Inspection | 33000 |  | Contract inspection | [8 empty] | Sewer Lateral Insert | 4000
3.04 | Material Testing | 0 |  | No paving | [8 empty] | Traffic Control / Day (Minor) | 1500
4.01 | Restoration | 0 |  | No restoration anticipated. | [8 empty] | Traffic Control / Day (Significant) | 3000
4.02 | Mitigation | 0 |  | No mitigation anticipated | [8 empty] | Traffic Control / Day (Caltrans) | 3500
5.01 | Mobilization | 47000 | [10 empty] | Point Repair Est. | 10000
5.02 | Traffic Control | 56000 | [10 empty] | Point Repair High GW | 15000
5.03 | Point Repairs | 37000 | [10 empty] | Inspection / Day | 1760
5.04 | CCTV Inspection and Pipe Preparation | 37000
5.05 | Sewer Main Lining | 620000
5.06 | Sewer Lateral Re-Establishment | 50000
5.07 | Sewer Lateral Insert | 132000
6.01 | Closeout, As-builts | 5000
| TOTAL | 1240000 | 0
| TOTAL 2--In-house Design | 1031000
| Design and Environmental | 75000
| Inspection and Construction Management | 180000
| Construction and Closeout | 984000
| Total Cost | 1239000

## Ojai ACP Rehab
City: ACP Golden West to Shady Ln
Item | Description - Trunk Sewer Rehab. (Ojai Trunk from S-30-07 to S-30-16) | Cost |  |  |  | 8in | 10in | 12in | 15in | 18in | 21in | 24in | Enter Values for Yellow Cells
1.01 | Design | 16000 |  | Small, simple design @ 5% | Length: | 0 | 0 | 0 | 1085 | 0 | 0 | 0 |  | 8in | 10in | 12in | 15in | 18in | 21in | 24in
1.02 | Environmental Design | 0 |  |  | CCTV: | 0 | 0 | 0 | 13020 | 0 | 0 | 0 | Rehab. Cost per Ft 2025 Estimate | 50 | 60 | 100 | 200 | 225 | 250 | 300
2.01 | Temporary and/or Permanent Easements | 0 |  | No easements anticipated | Rehab: | 0 | 0 | 0 | 217000 | 0 | 0 | 0 | CCTV/Prep Cost per Ft 2025 Estimate | 10 | 10 | 10 | 12 | 15 | 15 | 20
2.02 | Permits (ROW, VCWPD, 401, 404, etc.) | 1000 |  | Assume each project is $1M and needs a $2,500 permit | [8 empty] | Avg prop line (dense) | 75
3.01 | Construction Management | 32000 |  | CM assistance at 10% | [8 empty] | Avg prop line (rural) | 200
3.02 | Construction Phase Services | 16000 |  | CPS at 5% | [8 empty] | Sewer Lateral Re-establishment | 1500
3.03 | Inspection | 14000 |  | Contract inspection | [8 empty] | Sewer Lateral Insert | 4000
3.04 | Material Testing | 0 |  | No paving | [8 empty] | Traffic Control / Day (Minor) | 1500
4.01 | Restoration | 0 |  | No restoration anticipated. | [8 empty] | Traffic Control / Day (Significant) | 3000
4.02 | Mitigation | 0 |  | No mitigation anticipated | [8 empty] | Traffic Control / Day (Caltrans) | 3500
5.01 | Mobilization | 15000 | [10 empty] | Point Repair Est. | 10000
5.02 | Traffic Control | 28000 | [10 empty] | Point Repair High GW or Complex | 15000
5.03 | Point Repairs | 16000 |  | High GW/Complex | [8 empty] | Inspection / Day | 1760
5.04 | CCTV Inspection and Pipe Preparation | 13000
5.05 | Sewer Main Lining | 217000
5.06 | Sewer Lateral Re-Establishment | 8000
5.07 | Sewer Lateral Insert | 22000
6.01 | Closeout, As-builts | 1000
| TOTAL | 400000 | 0
| Design and Environmental | 17000
| Inspection and Construction Management | 62000
| Construction and Closeout | 320000
| Total Cost | 399000

## 2026-27 Summary
| Project | Estimated Cost | Rolling Exp
1 | Survey and feasibility design to replace 14” ACP west riverbank of Ventura River downstream of Baldwin | 150000 | 150000
2 | Techite trunk 1,800 LF CIPP | 560000 | 710000
3 | Rancho Dr sewer rehab | 580000 | 1290000
4 | Alto Dr sewer rehab | 710000 | 2000000 | 177000
5 | Feliz Dr sewer rehab | 190000 | 2190000 | 215000
392000
TOTAL C/S Transfer |  | 2190000

## 2025-2026 summary
Burnham&Kunkle CIPP | 759000
Spot Rairs | 117000
Easement | 27000
Fine Screen Replacment | 500000
Roofing | 287000
Roofing | 118000
HCAC | 30000
TOTAL | 1838000